## Sheet1
Status of greenery and beautification works in A.P. Urban Greening and Beautification Corporation Ltd.
ULB |  | Sl no | Name of the work | Work details | Status of works | Name of the Architects | Estimated amount (Rs. In lakhs) | Scheme
North Zone
1 | GVMC | 1 | Beautification of Traffic Islands & Central median | Traffic Islands - 24 | Contractors are identified by calling the tenders and execution of works are under progress | M/s Sumanjali landscape architects, Hyderabad. | 132.36 | GVMC funds
Road medians - 14
Road side open spaces - 2 nos.
|  | 2 | Beautificaton of central median at National Highway | Length of central median about 14.5 kilometers | Under progress | M/s Raghuraman Architects, chennai. | 452 | GVMC funds
|  | 3 | Beautification of 6 parks along beach road | GVMC park | Except Gokul & Lumbini park for other 5 parks works are in progress | M/s Raghuraman Architects, chennai. | 88.81 | GVMC funds
Gokul park
Sculpture park
R.K. Beach park
Childrens park
|  | 4 | Development of Major Park | Lumbini park | Designs are in process of preparation | M/s Sobhan Architects, Visakhapatnam. | 107 | AMRUT
|  | 5 | Development of parks | Lawsons bay park- 4.04 Acrs | ETS survey is completed |  |  | GVMC funds
Gajuwaka HB Colony park - 4.80 Acres
Sivaji Park - 10.00 Acres
|  | 6 | Development of water tank bund | Gajuwaka revula cheruvvu an extent of 23.24 acres | ETS survey is completed |  |  | GVMC funds
|  | 7 | Beautification of Tagarapuvalasa cheruvu | The water body is extended upto 35.13 acres area. | ETS survey is completed | M/s Sobhan Architects, Visakhapatnam. |  | GVMC funds
|  | 8 | Development of Green Belt area's in National Highway | 14.5 km Stretch | Works completed | APUG&BCL | 90 | GVMC funds
|  | 9 | Development of service road medians of National Highway | Plantation | Works completed | APUG&BCL | 25 | GVMC funds
|  | 10 | Beautification under flyover from MES junction to Railway station | Length of the median is1100 meters | works are in progress | M/s Sumanjali landscape architects, Hyderabad. | 175 | GVMC funds
|  | 11 | Beautification of open spaces | Thadichetlapalem to railway station road | Works under progress | M/s Sumanjali landscape architects, Hyderabad. | 12.87 | GVMC funds
|  |  |  | Costal battery to Park hotel opposite open spaces |  |  | 27.24
|  | 12 | APTDC beach road open spaces | Rk beach to Park hotel opposite open spaces | Tenders called for | APUG&BCL | 82.77 | GVMC funds
2 | Rajahmundry | 13 | Beautification of Central medians, Traffic islands. | Traffic Islands - 18, Length of central median about(4nos) - 3.46 Km & Side pockets | Works are completed | APUG&BCL | 771.67 | Mpl. Corpn. Funds
|  | 14 | Development of Water Body | Aryapuram tank -5.77Acres | Designs are in process of preparation | M/s Sobhan Architects, Visakhapatnam. | 50 | AMRUT
3 | Kakinada | 15 | Beautification of Central medians, Traffic islands & canal bunds | Traffic Islands - 18, Length of central median about(4nos) - 3.46 Km & canal bunds | Works Executed, Except canal bunds. | APUG&BCL | 56.84 | Mpl. Corpn. Funds
|  | 16 | Beautification of Traffic Islands & Central median | Traffic Islands - 13; Central medians | Designs, BOQs are in process of preparation | APUG&BCL |  | Mpl. Corpn. Funds
|  | 17 | Development of Parks | Rajaram colony park - 2.55 Acres | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 75 | AMRUT
|  | 18 | 6 parks in Kakinada Municipal Corporation are proposed for refurbishment | Raja tank - 25.54 Acres | Designs, BOQs and Estimates submitted to Municipal Corporation | M/s Sumanjali landscape architects, Hyderabad. | 1114 | Mpl. Corpn. Funds
Annamghati Cheruvu - 5.5 Acres
Gandhi Park - 5.8 Acres
Janmabhoomi Park - 2.36 Acres
Boats club - 30.62 Acres
Suresh Nagar Park - 5.73 Acres
4 | Eluru | 19 | Development of Colony parks | Postal colony park - 3.20 Acres | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 50 | AMRUT
|  | 20 | Development of Central medians & Block plantation. | Central medians - 2.4 KM | works are in progress | APUG&BCL | 16 | Mpl. Corpn. Funds
Block plantation - 4.00 Acres
5 | Srikakulam | 21 | Development of Colony parks | Shanthi Nagar park - 1.11 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
6 | Vizianagaram | 22 | Development of Pedda cheruvu | The water body is extended upto 5.9 acres area and the park includes with aminities like Yoga centre, boat club, gymansium, canteen. | Designs are in process of preparation | M/s Sobhan Architects, Visakhapatnam | 50 | AMRUT
7 | Kovvuru | 23 | Beautification of Central medians | Length of central media about 2.50 kilometers, side pockets plantation. | Works Executed, during Godavari Maha Pushkarams. | APUG&BCL | 42 | Municipality funds
|  | 24 | Beautification of Traffic Islands | Traffic islands located between kovuuru municipality and Rajahmundry National Highway. | Works Executed, during Godavari Maha Pushkarams. | APUG&BCL |  | Municipality funds
8 | Palakollu | 25 | Development of Ramagundam park. | The park is having an area about 2.5 Acres | Designs, BOQs and Estimates are handed over to the muncipal commissioner for execution. | M/s Sobhan Architects, Visakhapatnam |  | Municipality funds
|  | 26 | Development of Simbuni Cheruvu | Beautification of Water body having an area 5.05 Acres | Designs, BOQs and Estimates are handed over to the muncipal commissioner for execution. | M/s Sobhan Architects, Visakhapatnam |  | Municipality funds
9 | Narsipatnam | 27 | Beautification of Water tanks | The Pedda cheruvu of an extent - 2.17 Acres | Designs and BOQs are under progress | APUG&BCL |  | Municipality funds
|  | 28 | Development of Nandanavanam park | The park is having an area of about 1.5 Acres | Designs and BOQs are under progress | APUG&BCL |  | Municipality funds
10 | Bobilli | 29 | Development of Water tank and park | Dumping yard - 3.08 Acres | ETS survey is completed |  |  | Municipality funds
Rani Mallamma Devi park - 8.07 Acres
Solid waste management park - 5.00 Acres
11 | Tadepalligudem | 30 | Devlopment of Colony parks | 11th ward colony park with an extent of 0.77 Acres | DPR prepared | APUG&BCL | 50 | AMRUT
|  | 31 | Development of water body | 22nd & 23rd ward Krishnudi cheruvu beautification | Designs, BOQs and estimates are prepared | APUG&BCL
12 | Visakhapatnam Port Trust (VPT) | 32 | Improvement and beautification of VPT | Beautification of Visakhapatnam Port Trust area including AOB Gate, Ayyapa Gate, DCZT Gate, Jubliee Gate, North Gate, Slipway Gate, WQ5 Gate. Central medians, Traffic Islands and Civil works | works are in progress | M/s Team One India Pvt. Ltd. Hyderabad. | 2000 | VPT
13 | Bhimavaram | 33 | Devlopment of Major and Colony parks | B.V. Raju Park - 5.00 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
Central zone
14 | Vijayawada | 34 | Beautification of Central medians, Traffic islands | Traffic islands - 14 | Works under progress | M/s Conifer Landscape Architects, Hyderabad. | 220.36 | VMC funds
Central medians - 44
|  | 35 | Beautification works from Ramavarappadu ring to Skew bridge | side pockets | Work completed | M/s Shilpa Architects | 250 | VMC funds
|  | 36 | Development of Rajiv Gandhi park | Beautification and re-development of park - 9.56 Acres | ETS survey is completed | M/s Raj Expedith Landscape Architects. |  | VMC funds
|  | 37 | Development of K.L.Rao Park | Beautification and re-development of park - 3.67 Acres | Allocated to the architect for preparing deisgns. | M/s Sumanjali landscape architects, Hyderabad. |  | VMC funds
|  | 38 | Beautification of Canal bunds | Bandar canal bund near VMC office | Works under progress | M/s. Shilpa Architects | 100 | VMC funds
|  | 39 | Refurbishment of Raghaviah park | Re-development of the park - 3.28 | Allocated to the architect for preparing deisgns. | M/s Sumanjali landscape architects, Hyderabad. |  | VMC funds
|  | 40 | Beautification of PWD grounds and development of walkways | Beautification of greenery and landscape development of the existing grounds - 8.69 Acres | ETS survey is completed | M/s Kishore D Pradhan Landscape Architects. |  | VMC funds
|  | 41 | Gulabi thota and open area along the side of the canal | Beautification of greenery and landscape development | Designs completed & Estimations are yet to be finalised | M/s Microscape Landscape consultants |  | VMC funds
|  | 42 | Beautification of side pockets near and opp. To Rajiv Gandhi park | Beautification of greenery and landscape development | ETS survey completed | M/s Raj Expedith |  | VMC funds
|  | 43 | Beautification of Major park | Thummalapalli Kalakshetram - 2.33 Acres | Designs are in process of preparation | M/s Shilpa Architects | 100 | AMRUT
15 | Guntur | 44 | Beautification of Central medians and Traffic islands | Central medians - 15 | Designs, BOQ's & Estimates are prepared and submitted to GMC.Tenders called up for 9 Central Medians. Works alloted to Lakshmi nursery kadiam. Works yet to be started. | APUG&BCL | 163.2 | Mpl. Corpn. Funds
Traffic islands - 12
|  | 45 | Development of Gandhi park | Beautification and development of park - 6.35 Acres | ETS survey is completed | M/s Raj Expedith Landscape Architects. |  | Mpl. Corpn. Funds
|  | 46 | Development of Koritepadu lake | Beautification and development of Koretipadu lake - 12.10 Acres | The Designs and BOQs are prepared and estimates under process | M/s. Fountain Head Architects Pvt. Ltd. Hyderabad. |  | Mpl. Corpn. Funds
|  | 47 | Urban rezuvination of ring road | Re-development of ring road (9KM) | The Designs and BOQs are prepared and estimates under process | M/s. Fountain Head Architects Pvt. Ltd. Hyderabad. | 4754 | Mpl. Corpn. Funds
|  | 48 | Development of Brindhavan lake | Beautification and development of the lake | The Designs and BOQs are prepared and estimates under process | M/s. Fountain Head Architects Pvt. Ltd. Hyderabad. | 163 | Mpl. Corpn. Funds
|  | 49 | Development of Gujjana gundla tank | Beautification and development of the lake | The Designs and BOQs are prepared and estimates under process | M/s. Fountain Head Architects Pvt. Ltd. Hyderabad. | 329 | Mpl. Corpn. Funds
|  | 50 | Refurbishment of Manasarovar park | Beautification and re-development of park | ETS survey is completed | M/s Kishore D Pradhan Landscape Architects. |  | Mpl. Corpn. Funds
|  | 51 | Beautification of Colony parks | Koritepadu park | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 50 | AMRUT
|  | 52 | Development of Budempadu Lake | Beautification and development of the tank area-46 acres | ETS survey to be taken up |  |  | Mpl. Corpn. Funds
|  | 53 | CM House Road Bits | Beautification and development of the side pockets | Designs & BOQs are prepared estimation is under process | APUG&BCL |  | Mpl. Corpn. Funds
16 | Ongole | 54 | Development of Colony parks | Park at Vuracheruvu | Designs are in process of preparation | M/s S.R. Associattes, Hyderabad. |  | Mpl. Corpn. Funds
|  | 55 | Development of Colony parks | Chenna Kesava swamy temple layout - 1.68 Acres | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 50 | AMRUT
17 | Nellore | 56 | Beautification of Central medians | Length of central media about 6.30 kilometers | Works started | APUG&BCL | 69.218 | Mpl. Corpn. Funds
|  | 57 | Beautification of Nellore Tank | Beautification and Development of Lake park at Nellore Tank | The APUGBCL has given powerpoint presentation about conceptual designs to stakeholders at Nellore | M/s S.R. Associattes | 1300 | DPR is to be prepared to enable to submit to the government for sanction.
|  |  |  | Beautification and Development of Public park near Summer Storage Tank |  |  | 200
|  |  |  | Development of walking path and Greenery on Summer storage Tank Bund |  |  | 200
|  |  |  | Development of Walkway with Green cover on Nellore Tank Bund |  |  | 300
|  | 58 | Development of Major Parks | Magunta layout - 6.16 Acres | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 50 | AMRUT
18 | Tenali | 59 | Beautification of Central medians | Central medians - 1.32 KM | Desings and BOQs are prepared and submitted to Municipality | APUG&BCL | 9.8 | Municipal funds
|  | 60 | Development of Colony parks | UDA Colony park - 1.12 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
19 | Gudivada | 61 | Development of Colony parks | Sri Tummala Rama brahmam park near I town police station(Park Road)-1.98acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
20 | Machilipatnam | 62 | Development of colony parks | Colony park at Sidimbi agraharam - 1.227 Acres | DPR prepared | APUG&BCL | 50 | AMRUT
21 | Narsaraopeta | 63 | Beautification of Central medians and Traffic islands | Central medians - 6 | Completed | APUG&BCL | 27.0057 | Municipality funds
Traffic Island - 1
|  |  |  | Burial Grounds |  |  | 4.73
|  | 64 | Development of Colony parks | NGO Colony park - 1.65 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
22 | Chilakaluripeta | 65 | Development of Colony parks | CR colony park - 1.93 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
|  | 66 | Beautification and Development of Landscape works for Central Medians | Central Medians | Tenders are called for | APUG&BCL | 14.23 | Municipality funds
South Zone
23 | Tirupati | 67 | Beautification of Central medians | Central medians at RC Road, Tilak Road to Sri Krishnadevaraya Statue, Tataiahgunta Road, YSR Circle to Tirumala Byepass Road | Work is completed | M/s Raghuraman Architects, chennai. | 15.6 | TUDA
|  | 68 | Development of Central Medians | From Ramanujam Circle to Arch | Designs and BOQs are prepared by APUG&BCL | APUG&BCL |  | TUDA
|  | 69 | Development of Jagajeevanram Park | Park is having an area of 3.5 Acres | Tenders Finalized | M/s Raghuraman Architects, chennai. | 37 | TUDA
|  | 70 | Development of Padmavathi Park, Bhairagipatteda. | Development of Padmavathi Park | Tenders Finalized | M/s Raghuraman Architects, chennai. | 6 | TUDA
|  | 71 | Development of Major Parks and Colony parks | Prakasham park (Municipal Centinery park) | Designs are in process of preparation | APUG&BCL | 75 | AMRUT
24 | Chittoor | 72 | Development of Major Parks and Colony parks | BV Reddy Park - 0.82 Acres | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 50 | AMRUT
|  | 73 | Beautification and Development of Kattamanchi cheruvu | The tank is extended upto an area of 3.06 acres | ETS survey is compeletd | APUG&BCL |  | Mpl. Corpn. Funds
25 | Kadapa | 74 | Development of Colony parks | Gazetted Officers Colony - 0.4 Acres | DPR prepared and submitted to Municipal Corporation | APUG&BCL | 50 | AMRUT
Housing Board Colony - 0.308 Acres
26 | Kurnool | 75 | Development of Colony park | Netaji Colony park - 0.75 Acres (Weaker section colony) | Designs, BOQs and estimates are prepared | M/s S.R. Associates | 50 | AMRUT
27 | Anantapur | 76 | Development of Colony park | Buddha vihar park - 0.59 Acres | DPR prepared | APUG&BCL | 50 | AMRUT
28 | Proddatur | 77 | Development of Major Park and Colony park | Major Park at L.P.No.35/2012/A, of Bollavaram. | DPR prepared and submitted to Municipality | M/s S.R. Associattes, Hyderabad. | 50 | AMRUT
|  | 78 | Development of Colony park at 3rd Colony | The 3rd colony park is having an area of 1.49 Acres | ETS survey yet to be done. | M/s S.R. Associattes & APUGBCL | 143.7 | Municipality funds
|  | 79 | Beautification of Central medians | 3 Central medians are having a length about 1.98 KM | The Designs and BOQs are prepared and submitted to Proddatur Municipality | APUG&BCL | 24.51 | Municipality funds
|  | 80 | Development of sports complex arena | Components like Indoor, outdoor games activities including swimming pool are incorporated besides all round walking track | The Designs are prepared and submitted to Municipality | M/s S.R. Associattes, Hyderabad. |  | Municipality funds
29 | Nandyala | 81 | Development of Major Parks and Colony parks | APHB park - 2.07 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
30 | Adoni | 82 | Development of Colony park | APHB colony park - 0.49 Acres | DPR prepared | APUG&BCL | 50 | AMRUT
|  | 83 |  | Nehuru peace park - 0.57 Acres | Designs are in process of preparation
31 | Madanapalli | 84 | Development of Colony parks | Ramnagar park - 2.85 Acres | DPR prepared and submitted to Municipality | APUG&BCL | 50 | AMRUT
32 | Hindupuram | 85 | Development of Major Parks and Colony parks | Surrappakunta as a Major Park - 8.78 Acres | Designs, BOQs and estimates are prepared | APUG&BCL | 50 | AMRUT
33 | Dharmavaram | 86 | Development of Colony parks | Siva nagar colony park - 0.46 Acres | DPR prepared | APUG&BCL | 50 | AMRUT
|  | 87 |  | Durga nagar colony park - 0.90 Acres | Designs, BOQs and estimates are prepared
34 | Gunthakal | 88 | Development of Major Parks and Colony parks | One Major Park at S.S. Tank area - 6.50 Acres | Designs, BOQs and estimates are prepared | APUG&BCL | 50 | AMRUT
35 | Tadipatri | 89 | Development of Major Parks | One Major Park at bund road area | Designs are in process of preparation | M/s S.R. Associattes, Hyderabad. | 50 | AMRUT
|  | 90 | River front park development | Beautfication and Rejuvination of the park | ETS survey is completed by Municipality, designs and BOQs are under progress. | M/s S.R. Associattes, Hyderabad. |  | Municipality funds
|  | 91 | Beautification and Development of Landscape works for Central Medians | Central Medians - 2.70 KM | Estimates submitted to the Municipal Commissioner | APUG&BCL | 140.28 | Municipality funds
36 | Srikalahasthi | 92 | Development of Recreation Park | Preparing conceptual deisgns for Pannagal Park | Works under progress | M/s S.R. Associattes, Hyderabad. | 32.8 | TUDA
37 | Puttaparthi | 93 | Beautification of Central medians and Avenues | Central medians - 6.5 KM; Length of avenue plantation is about 8 Kilometers | Central Medians and Avenue Plantation works are completed | APUG&BCL | 111.58 | Municipality funds
Raising of Central Nurseries
38 | Guntur | 94 | Development of Nursery | The nursery is planned for raising 5 Lakhs sapplings | DPR is sent to the government for sanction | APUG&BCL | 700 | File is circulated to the Govt for release of funds from APUFIDC.
39 | Simhachalam | 95 | Development of Nursery | The nursery is planned for raising 5 Lakhs sapplings | GO issued allocating an area of 120 acres near simhchalam. Authorization issued by the Managing Director to Zonal Manager,North Zone, Visakhapatnam, to take over Nursery land from EO, simhachalam. Jungle clearence operation with machines is under progress for further development | APUG&BCL | 700 | File is circulated to the Govt for release of funds from APUFIDC.
40 | Srikalahasthi | 96 | Development of Nursery | The nursery is planned for raising 5 Lakhs sapplings at AMR puttur tank | The Government of A.P. Released a G.O.RT.No.967 stating that sanction of 25 acres land for development of nursery. | M/s S.R. Associattes, Hyderabad. | 700 | APUFIDC
Endowments Department works
41 | Simhachalam Temple | 97 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | M/s Sobhan Architects | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department
42 | Annavaram Temple | 98 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | APUG&BCL | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department
43 | Dwaraka Tirumala | 99 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | APUG&BCL | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department
44 | Kanakadurga Temple | 100 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | APUG&BCL | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department
45 | Kanipakam Temple | 101 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | APUG&BCL | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department
46 | Srikalahasti Temple | 102 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | M/s Ravikumar and Associates | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department
|  | 103 | Beautification and development of Lowbhavi area | Development and landscape works of walkway around water body and open spaces.
47 | Srisailam Temple | 104 | Beautification and landscape development of temple | Greenery development, beautification and landscape development in temple. | Designs, BOQs and estimates are prepared | M/s S.R. Associates | The estimate amount will be arrived once the designs BOQs are prepared. | Endowments department